## pivot_data
Row Labels | incidents by application
Employee Portal | 4
Grand Total | 4
[5 empty] | Row Labels | incident distribution by priority
[5 empty] | P1 | 1
[5 empty] | P2 | 3
[5 empty] | Grand Total | 4
|  | SLA_Status | Breached
|  | Row Labels | sla breaches by application
|  | Employee Portal | 4
|  | Grand Total | 4
[5 empty] | Row Labels | Average of Resolution_Time by category
[5 empty] | Database | 7
[5 empty] | Network | 9.3333
[5 empty] | Grand Total | 8.75
|  |  | Row Labels | top root causes
|  |  | DB Connection Failure | 1
|  |  | DNS Failure | 3
|  |  | Grand Total | 4
[6 empty] | Row Labels | incident trend over time
[6 empty] | 2026-06-06 | 1
[6 empty] | 2026-06-11 | 1
[6 empty] | 2026-06-16 | 1
[6 empty] | 2026-06-26 | 1
[6 empty] | Grand Total | 4
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## incidents_data
Incident_ID | Opened_Date | Resolved_Date | Application | Category | Priority | Status | Assigned_Team | Root_Cause | Resolution_Time_Hours | SLA_Target_Hours | SLA_Status | Users_Affected | Resolution_Notes | Month | SLA_diff_hours | support_level
INC-1001 | 2026-06-01 | 2026-06-01 | Employee Portal | Login | P2 | Resolved | L1 Support | Password Expired | 2 | 4 | Met | 18 | Password reset and account unlocked | Jun 2026 | -2 | L2/L3
INC-1002 | 2026-06-01 | 2026-06-02 | Payment Gateway | API | P1 | Resolved | Application Team | API Timeout | 7 | 4 | Breached | 450 | API service restarted after validation | Jun 2026 | 3 | L1
INC-1003 | 2026-06-02 | 2026-06-02 | HRMS | Access | P3 | Closed | L1 Support | Missing User Role | 5 | 8 | Met | 1 | Access granted after approval | Jun 2026 | -3 | L2/L3
INC-1004 | 2026-06-02 | 2026-06-03 | Customer Portal | Performance | P2 | Resolved | Application Team | Server Overload | 9 | 8 | Breached | 120 | Service capacity issue escalated | Jun 2026 | 1 | L1
INC-1005 | 2026-06-03 | 2026-06-03 | Employee Portal | Network | P3 | Resolved | Network Team | DNS Failure | 3 | 8 | Met | 35 | DNS cache and routing issue fixed | Jun 2026 | -5 | L2/L3
INC-1006 | 2026-06-03 | 2026-06-04 | CRM | Database | P1 | Resolved | Database Team | DB Lock | 6 | 4 | Breached | 280 | Blocking query identified and resolved | Jun 2026 | 2 | L2/L3
INC-1007 | 2026-06-04 | 2026-06-04 | HRMS | Login | P4 | Closed | L1 Support | Password Expired | 1 | 24 | Met | 1 | Password reset completed | Jun 2026 | -23 | L2/L3
INC-1008 | 2026-06-04 | 2026-06-05 | Customer Portal | API | P2 | Resolved | Application Team | API Timeout | 6 | 8 | Met | 95 | API configuration corrected | Jun 2026 | -2 | L1
INC-1009 | 2026-06-05 | 2026-06-05 | Payment Gateway | Performance | P1 | Resolved | Application Team | Server Overload | 3 | 4 | Met | 600 | High CPU process restarted as per runbook | Jun 2026 | -1 | L2/L3
INC-1010 | 2026-06-05 | 2026-06-06 | CRM | Access | P3 | Closed | L1 Support | Missing User Role | 7 | 8 | Met | 2 | Role assigned after manager approval | Jun 2026 | -1 | L2/L3
INC-1011 | 2026-06-06 | 2026-06-07 | Employee Portal | Network | P2 | Resolved | Network Team | DNS Failure | 10 | 8 | Breached | 75 | DNS server issue escalated and resolved | Jun 2026 | 2 | L1
INC-1012 | 2026-06-06 | 2026-06-06 | HRMS | Database | P3 | Resolved | Database Team | DB Lock | 4 | 8 | Met | 20 | Long-running query optimized | Jun 2026 | -4 | L2/L3
INC-1013 | 2026-06-07 | 2026-06-07 | Customer Portal | Login | P3 | Resolved | L1 Support | Password Expired | 3 | 8 | Met | 12 | User credentials reset successfully | Jun 2026 | -5 | L2/L3
INC-1014 | 2026-06-07 | 2026-06-08 | Payment Gateway | Database | P1 | Resolved | Database Team | DB Connection Failure | 8 | 4 | Breached | 520 | Database connection pool restarted | Jun 2026 | 4 | L1
INC-1015 | 2026-06-08 | 2026-06-08 | CRM | Performance | P2 | Resolved | Application Team | Memory Leak | 6 | 8 | Met | 150 | Application service restarted | Jun 2026 | -2 | L2/L3
INC-1016 | 2026-06-08 | 2026-06-09 | HRMS | Access | P2 | Resolved | L1 Support | Approval Delay | 10 | 8 | Breached | 8 | Access approved after escalation | Jun 2026 | 2 | L2/L3
INC-1017 | 2026-06-09 | 2026-06-09 | Employee Portal | API | P3 | Closed | Application Team | API Timeout | 5 | 8 | Met | 40 | API endpoint response improved | Jun 2026 | -3 | L1
INC-1018 | 2026-06-09 | 2026-06-10 | Customer Portal | Network | P1 | Resolved | Network Team | Firewall Block | 7 | 4 | Breached | 310 | Firewall rule updated after review | Jun 2026 | 3 | L2/L3
INC-1019 | 2026-06-10 | 2026-06-10 | Payment Gateway | Login | P2 | Resolved | L1 Support | Account Locked | 2 | 4 | Met | 65 | Locked accounts unlocked in bulk | Jun 2026 | -2 | L2/L3
INC-1020 | 2026-06-10 | 2026-06-11 | CRM | Database | P2 | Resolved | Database Team | DB Lock | 9 | 8 | Breached | 175 | Deadlock removed and query tuned | Jun 2026 | 1 | L1
INC-1021 | 2026-06-11 | 2026-06-11 | HRMS | Performance | P3 | Resolved | Application Team | High CPU Usage | 4 | 8 | Met | 30 | Background job rescheduled | Jun 2026 | -4 | L2/L3
INC-1022 | 2026-06-11 | 2026-06-12 | Employee Portal | Network | P2 | Resolved | Network Team | DNS Failure | 9 | 8 | Breached | 90 | DNS configuration corrected | Jun 2026 | 1 | L2/L3
INC-1023 | 2026-06-12 | 2026-06-12 | Customer Portal | Access | P4 | Closed | L1 Support | Missing User Role | 2 | 24 | Met | 3 | Required role assigned | Jun 2026 | -22 | L2/L3
INC-1024 | 2026-06-12 | 2026-06-13 | Payment Gateway | API | P1 | Resolved | Application Team | API Timeout | 6 | 4 | Breached | 780 | Payment API service restarted | Jun 2026 | 2 | L1
INC-1025 | 2026-06-13 | 2026-06-13 | CRM | Login | P3 | Resolved | L1 Support | Password Expired | 4 | 8 | Met | 10 | Password reset completed | Jun 2026 | -4 | L2/L3
INC-1026 | 2026-06-13 | 2026-06-14 | HRMS | Database | P2 | Resolved | Database Team | Slow Query | 9 | 8 | Breached | 55 | Query index added and validated | Jun 2026 | 1 | L1
INC-1027 | 2026-06-14 | 2026-06-14 | Employee Portal | Performance | P3 | Resolved | Application Team | Memory Leak | 5 | 8 | Met | 70 | Service restarted and monitored | Jun 2026 | -3 | L2/L3
INC-1028 | 2026-06-14 | 2026-06-15 | Customer Portal | Network | P1 | Resolved | Network Team | Load Balancer Failure | 8 | 4 | Breached | 400 | Load balancer node replaced | Jun 2026 | 4 | L2/L3
INC-1029 | 2026-06-15 | 2026-06-15 | Payment Gateway | Access | P2 | Resolved | L1 Support | Missing User Role | 3 | 4 | Met | 15 | Merchant access role updated | Jun 2026 | -1 | L2/L3
INC-1030 | 2026-06-15 | 2026-06-16 | CRM | API | P2 | Resolved | Application Team | API Timeout | 10 | 8 | Breached | 210 | API gateway settings corrected | Jun 2026 | 2 | L1
INC-1031 | 2026-06-16 | 2026-06-16 | HRMS | Login | P4 | Closed | L1 Support | Account Locked | 2 | 24 | Met | 1 | Account unlocked after verification | Jun 2026 | -22 | L2/L3
INC-1032 | 2026-06-16 | 2026-06-17 | Employee Portal | Database | P1 | Resolved | Database Team | DB Connection Failure | 7 | 4 | Breached | 230 | Database service restored | Jun 2026 | 3 | L1
INC-1033 | 2026-06-17 | 2026-06-17 | Customer Portal | Performance | P2 | Resolved | Application Team | Server Overload | 7 | 8 | Met | 180 | Additional server instance enabled | Jun 2026 | -1 | L2/L3
INC-1034 | 2026-06-17 | 2026-06-18 | Payment Gateway | Network | P2 | Resolved | Network Team | Firewall Block | 9 | 8 | Breached | 260 | Network policy updated | Jun 2026 | 1 | L2/L3
INC-1035 | 2026-06-18 | 2026-06-18 | CRM | Access | P3 | Closed | L1 Support | Approval Delay | 6 | 8 | Met | 4 | Approval received and role assigned | Jun 2026 | -2 | L2/L3
INC-1036 | 2026-06-18 | 2026-06-19 | HRMS | API | P1 | Resolved | Application Team | API Timeout | 5 | 4 | Breached | 330 | API service restarted after log review | Jun 2026 | 1 | L1
INC-1037 | 2026-06-19 | 2026-06-19 | Employee Portal | Login | P2 | Resolved | L1 Support | Password Expired | 3 | 4 | Met | 45 | Password reset through self service | Jun 2026 | -1 | L2/L3
INC-1038 | 2026-06-19 | 2026-06-20 | Customer Portal | Database | P2 | Resolved | Database Team | DB Lock | 9 | 8 | Breached | 110 | Blocking transaction rolled back | Jun 2026 | 1 | L1
INC-1039 | 2026-06-20 | 2026-06-20 | Payment Gateway | Performance | P3 | Resolved | Application Team | High CPU Usage | 6 | 8 | Met | 220 | Unnecessary batch job stopped | Jun 2026 | -2 | L2/L3
INC-1040 | 2026-06-20 | 2026-06-21 | CRM | Network | P1 | Resolved | Network Team | DNS Failure | 8 | 4 | Breached | 350 | DNS failover activated | Jun 2026 | 4 | L2/L3
INC-1041 | 2026-06-21 | 2026-06-21 | HRMS | Access | P3 | Closed | L1 Support | Missing User Role | 4 | 8 | Met | 2 | Role assigned after approval | Jun 2026 | -4 | L2/L3
INC-1042 | 2026-06-21 | 2026-06-22 | Employee Portal | API | P2 | Resolved | Application Team | API Timeout | 7 | 8 | Met | 85 | Endpoint timeout limit increased | Jun 2026 | -1 | L1
INC-1043 | 2026-06-22 | 2026-06-22 | Customer Portal | Login | P4 | Closed | L1 Support | Account Locked | 1 | 24 | Met | 1 | Account unlocked successfully | Jun 2026 | -23 | L2/L3
INC-1044 | 2026-06-22 | 2026-06-23 | Payment Gateway | Database | P1 | Resolved | Database Team | Slow Query | 6 | 4 | Breached | 670 | Database index rebuilt | Jun 2026 | 2 | L1
INC-1045 | 2026-06-23 | 2026-06-23 | CRM | Performance | P2 | Resolved | Application Team | Memory Leak | 5 | 8 | Met | 145 | Service restarted after memory analysis | Jun 2026 | -3 | L2/L3
INC-1046 | 2026-06-23 | 2026-06-24 | HRMS | Network | P2 | Resolved | Network Team | Firewall Block | 9 | 8 | Breached | 60 | Firewall port opened after approval | Jun 2026 | 1 | L2/L3
INC-1047 | 2026-06-24 | 2026-06-24 | Employee Portal | Access | P3 | Closed | L1 Support | Approval Delay | 5 | 8 | Met | 6 | Access granted after manager confirmation | Jun 2026 | -3 | L2/L3
INC-1048 | 2026-06-24 | 2026-06-25 | Customer Portal | API | P1 | Resolved | Application Team | API Timeout | 8 | 4 | Breached | 500 | API deployment rolled back | Jun 2026 | 4 | L1
INC-1049 | 2026-06-25 | 2026-06-25 | Payment Gateway | Login | P2 | Resolved | L1 Support | Password Expired | 2 | 4 | Met | 80 | Passwords reset for impacted users | Jun 2026 | -2 | L2/L3
INC-1050 | 2026-06-25 | 2026-06-26 | CRM | Database | P2 | Resolved | Database Team | DB Lock | 10 | 8 | Breached | 190 | Transaction issue resolved | Jun 2026 | 2 | L1
INC-1051 | 2026-06-26 | 2026-06-26 | HRMS | Performance | P3 | Resolved | Application Team | Server Overload | 4 | 8 | Met | 25 | Application cache cleared | Jun 2026 | -4 | L2/L3
INC-1052 | 2026-06-26 | 2026-06-27 | Employee Portal | Network | P2 | Resolved | Network Team | DNS Failure | 9 | 8 | Breached | 100 | DNS records corrected | Jun 2026 | 1 | L2/L3
INC-1053 | 2026-06-27 | 2026-06-27 | Customer Portal | Access | P4 | Closed | L1 Support | Missing User Role | 2 | 24 | Met | 2 | Access role mapped successfully | Jun 2026 | -22 | L2/L3
INC-1054 | 2026-06-27 | 2026-06-28 | Payment Gateway | API | P1 | Resolved | Application Team | API Timeout | 7 | 4 | Breached | 720 | API cluster restarted | Jun 2026 | 3 | L1
INC-1055 | 2026-06-28 | 2026-06-28 | CRM | Login | P3 | Resolved | L1 Support | Account Locked | 3 | 8 | Met | 9 | Account unlocked after identity verification | Jun 2026 | -5 | L2/L3
INC-1056 | 2026-06-28 | 2026-06-29 | HRMS | Database | P2 | Resolved | Database Team | DB Connection Failure | 9 | 8 | Breached | 48 | Database listener restarted | Jun 2026 | 1 | L1
INC-1057 | 2026-06-29 | 2026-06-29 | Employee Portal | Performance | P3 | Resolved | Application Team | High CPU Usage | 5 | 8 | Met | 55 | Background service optimized | Jun 2026 | -3 | L2/L3
INC-1058 | 2026-06-29 | 2026-06-30 | Customer Portal | Network | P1 | Resolved | Network Team | Load Balancer Failure | 6 | 4 | Breached | 390 | Traffic routed to standby node | Jun 2026 | 2 | L2/L3
INC-1059 | 2026-06-30 | 2026-06-30 | Payment Gateway | Access | P2 | Resolved | L1 Support | Approval Delay | 3 | 4 | Met | 11 | Access approved and enabled | Jun 2026 | -1 | L2/L3
INC-1060 | 2026-06-30 | 2026-07-01 | CRM | API | P2 | Resolved | Application Team | API Timeout | 9 | 8 | Breached | 205 | API configuration updated and tested | Jun 2026 | 1 | L1

## dashboard
Application Support Incident & SLA Analytics Dashboard
total incidents |  | SLA compliance | avg resolution time | critical p1 incidents | total users affected
60 |  | 0.55 | 5.8167 | 14 | 9674
Key Insights: • Tracks incident volume, critical incidents, and affected users. • Measures SLA compliance and identifies applications with SLA breaches. • Identifies recurring root causes for faster troubleshooting and escalation. • Supports data-driven application support decisions.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.